## Localization
S.NO | SIE | Project | PN | Family | Group | Tier | Priority | Supply region | Supplier Name & Location | RFQ send date | DFM close date | Biz award date | Line installation date | Line readiness date | First off process date | C exit date | TQP date | Risk Level | GSM | SCPM | Next step plan | Action Items for Cindy
1 | Bryn Pearce | HVS 1BC |  | 1BC | HV | 1 | P1 |  | Quanta SH |  |  | 2024-05-18 |  | 2024-08-24 |  |  | 2025-01-07 | Closed | Kevin |  | Next step for 1 | action items for cindy
2 | Bryn Pearce | HVS 1BC 2 |  | 1BC | HV | 1 | P1 |  | Song Chuan TW/MX |  |  | 2024-04-12 |  | 2024-09-07 |  |  | 2025-01-21 | Low | Kevin |  | Next step for 2 | action items for cindy 2
3 | Bryn Pearce | AYSNC A, asfasdf , HVS 1BC |  | 1BC | HV | 1 | P1 |  | Quanta SH |  |  | 2024-05-18 |  | 2024-08-24 |  |  | 2025-01-07 | Closed | Kevin |  | Next step for 3 | action items for cindy 3
4 | Sateria Salim | CHAGEPORT, NA |  | Charging | HV | 1 | P1 |  | Pegatron TW | 2024-04-04 | 2024-06-03 | 2024-07-31 |  | 2025-01-30 |  |  | 2025-02-15 | High | Zon |  | Next step for 4 | action items for cindy 4
5 | Xingjian Bi | NPI blabla |  | blabla | HV | 1 | P1 |  | Pegatron TW | 2024-04-14 | 2024-07-03 | 2024-08-31 |  | 2025-01-29 |  |  | 2025-02-17 | High | Zon |  | coding coding coding coding again | blablabla

## Others
S.NO | SIE | Project | PN | Family | Group | Tier | Priority | Supply region | Supplier Name & Location | RFQ send date | DFM close date | Biz award date | Line installation date | Line readiness date | First off process date | C exit date | TQP date | Risk Level | GSM | SCPM | Next step plan | Action Items for Cindy
1 | Bryn Pearce | HVS 1BC |  | 1BC | HV | 1 | P1 |  | Quanta SH |  |  | 2024-05-18 |  | 2024-08-24 |  |  | 2025-01-07 | Closed | Kevin |  | Next step for 1 | action items for cindy
2 | Bryn Pearce | HVS 1BC |  | 1BC | HV | 1 | P1 |  | Song Chuan TW/MX |  |  | 2024-04-12 |  | 2024-09-07 |  |  | 2025-01-21 | Low | Kevin |  | Next step for 2 | action items for cindy 2
3 | Bryn Pearce | AYSNC A, asfasdf , HVS 1BC |  | 1BC | HV | 1 | P1 |  | Quanta SH |  |  | 2024-05-18 |  | 2024-08-24 |  |  | 2025-01-07 | Closed | Kevin |  | Next step for 3 | action items for cindy 3
4 | Sateria Salim | CHAGEPORT, NA |  | Charging | HV | 1 | P1 |  | Pegatron TW | 2024-04-04 | 2024-06-03 | 2024-07-31 |  | 2025-01-30 |  |  | 2025-02-15 | High | Zon |  | Next step for 4 | action items for cindy 4

## Energy
S.NO | SIE | Project | PN | Family | Group | Tier | Priority | Supply region | Supplier Name & Location | RFQ send date | DFM close date | Biz award date | Line installation date | Line readiness date | First off process date | C exit date | TQP date | Risk Level | GSM | SCPM | Next step plan | Action Items for Cindy
1 | Bryn Pearce | HVS 1BC |  | 1BC | HV | 1 | P1 |  | Quanta SH |  |  | 2024-05-18 |  | 2024-08-24 |  |  | 2025-01-07 | Closed | Kevin |  | Next step for 1 | action items for cindy
2 | Bryn Pearce | HVS 1BC 2 |  | 1BC | HV | 1 | P1 |  | Song Chuan TW/MX |  |  | 2024-04-12 |  | 2024-09-07 |  |  | 2025-01-21 | Low | Kevin |  | Next step for 2 | action items for cindy 2
3 | Bryn Pearce | AYSNC A, asfasdf , HVS 1BC |  | 1BC | HV | 1 | P1 |  | Quanta SH |  |  | 2024-05-18 |  | 2024-08-24 |  |  | 2025-01-07 | Closed | Kevin |  | Next step for 3 | action items for cindy 3
4 | someone | CHAGEPORT, NA |  | Charging | HV | 1 | P1 |  | Pegatron TW | 2024-04-04 | 2024-06-03 | 2024-07-19 |  | 2025-01-30 |  |  | 2025-02-15 | High | Zon |  | Next step for 4 | action itemenergy aasdfas for cindy 4